## Sheet1
CLASS 22 HOTEL 69 REUNION TIMELINE
ACTIVITY | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT
Request Intial Deposit $50 From Attendees | MAR: 18
Initial Deposit Due | MAR: 26
Cropped Photos of Deceased on Web Site | APR: 16
Tour/Activities Survey To Attendees | MAY: 7
Tour/Activities Survey Due | MAY: 21
Security Forms For White House Tour - Sent | JUL: 8
Security Forms For White House Tour - Due | JUL: 11
Order Wreaths - Palace Florists | JUL: 10
Request Army Patches From Attendees | AUG: 10
Final Payment Due From Attendees | bar: SEP
Request For Biographical Information | bar: SEP
Sheraton Hotel Reservation Deadline | SEP: 3
Order Name Badges My Reunion Tags | SEP: 4
Order Lapel Pins - Lapel Pin Zone | SEP: 4
Request Memorabilia | SEP: 5
Schedule Transportation - Bus and All | SEP: 5
Army Patches Due | SEP: 7
Banquet Program To Sheraton | SEP: 22
Finalyze Videos | SEP: 15
Biographical Information Due | SEP: 17
Palace Florist - Insert For Wreath | SEP: 18
Final Payment To Sheraton Hotel | SEP: 20
Arlington Visitor Bureau - Bags and Maps | SEP: 27
Meeting Planning Guide for Arlington | SEP: 27
Order Leis From Amazon
Banquet Event Order Due | OCT: 2
Hotel Registration Deadline | OCT: 3
Ft Belvoir DPTMS - Loan of Flags and Staffs | OCT: 3 or 4
Reunion Events | OCT: 4
Reunion Events | OCT: 5
Reunion Ends | OCT: 6
Reunion Survey To Attendees | OCT: 10
Ft. Belvoir Eagle - Article | OCT: 14
Reunion Survey Due | OCT: 17
After Action Report | OCT: 20